## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
0RR3oJXcU02NULKPL88sRckAE1AL | Deploy_Backend_Version-01 | Pilot & Deployment | Completed | Medium | MEYRUSHAN N it22564818 | MEYRUSHAN N it22564818 | 03/08/2026 |  | 02/25/2026 | false | false | 03/08/2026 | MEYRUSHAN N it22564818
CvFmSvh_KkeTjkaC1Uvh8skAKvTT | Deploy_Frontend_Version-02 | Pilot & Deployment | Completed | Medium | MEYRUSHAN N it22564818 | MEYRUSHAN N it22564818 | 03/08/2026 |  | 02/25/2026 | false | false | 03/08/2026 | MEYRUSHAN N it22564818
E8_XQTez1kGl0iEY2iN4-skABDY6 | Draft preliminary software specifications | Analysis/Software requirements | Completed | Medium |  | MEYRUSHAN N it22564818 | 03/04/2026 |  |  | false | false | 03/04/2026 | MEYRUSHAN N it22564818 |  |  | Pink
Gc8te5mzZU-hjc7KXapdrMkAAluT | Fintenss_Component_Test | Testing | Completed | Medium | LAXSHIKA.S it22596802 | MEYRUSHAN N it22564818 | 03/08/2026 |  | 02/22/2026 | false | false | 03/08/2026 | LAXSHIKA.S it22596802
HFE-AIKcP02GkVr_Az4IockAElgX | Conduct user testing | Design | Completed | Important |  | MEYRUSHAN N it22564818 | 03/04/2026 |  |  | false | false | 03/08/2026 | MEYRUSHAN N it22564818 |  |  | Yellow
HKgaScSQPE6BHWg7DqJABckAK8Fp | Backend Devlopement | Development | Completed | Medium | KAVILAKSHAN V it22116338;LAXSHIKA.S it22596802;MEYRUSHAN N it22564818 | MEYRUSHAN N it22564818 | 03/08/2026 |  | 01/14/2026 | false | false | 03/08/2026 | KAVILAKSHAN V it22116338
Kqno2noGlUmgSETyDzsy-ckAMYVg | Backend_Intergartion | Development | Completed | Medium | KAVILAKSHAN V it22116338;LAXSHIKA.S it22596802;MEYRUSHAN N it22564818 | MEYRUSHAN N it22564818 | 03/08/2026 |  | 02/12/2026 | false | false | 03/08/2026 | MEYRUSHAN N it22564818
QSg_3vNT20GrXH5UDrS5JMkAC25J | Model Devlopment_Mentel_Heath_Component | Design | Completed | Medium | KAVILAKSHAN V it22116338 | MEYRUSHAN N it22564818 | 03/04/2026 |  | 10/11/2025 | false | false | 03/05/2026 | KAVILAKSHAN V it22116338
Qv5MZ2kJgUuSiOW-Yx7XOckAPaoc | Identify the Frontend Requirements | Analysis/Software requirements | Completed | Medium | KAVILAKSHAN V it22116338;LAXSHIKA.S it22596802;MEYRUSHAN N it22564818 | MEYRUSHAN N it22564818 | 03/04/2026 |  | 10/10/2025 | false | false | 03/08/2026 | LAXSHIKA.S it22596802
RzJmPMwv9U6iASYRamCppMkAJvdR | Frontend Devlopment | Development | Completed | Medium | KAVILAKSHAN V it22116338;LAXSHIKA.S it22596802;MEYRUSHAN N it22564818 | MEYRUSHAN N it22564818 | 03/08/2026 |  | 01/20/2026 | false | false | 03/08/2026 | MEYRUSHAN N it22564818
VcjFMYCu7EyuLH969HSB6skALW-t | Frontend_Intergration | Development | Completed | Medium | KAVILAKSHAN V it22116338;LAXSHIKA.S it22596802;MEYRUSHAN N it22564818 | MEYRUSHAN N it22564818 | 03/08/2026 |  | 02/12/2026 | false | false | 03/08/2026 | KAVILAKSHAN V it22116338
_r6tjazRbk2WsLiEYp3KEckAE_GG | Identify the Backend Requirements | Analysis/Software requirements | Completed | Medium | KAVILAKSHAN V it22116338;LAXSHIKA.S it22596802;MEYRUSHAN N it22564818 | MEYRUSHAN N it22564818 | 03/04/2026 |  | 10/10/2025 | false | false | 03/05/2026 | KAVILAKSHAN V it22116338
aSlod2SoWEm6-hAy9H6qiskACmBE | Conduct testing | Testing | Completed | Important |  | MEYRUSHAN N it22564818 | 03/04/2026 |  |  | false | false | 03/08/2026 | MEYRUSHAN N it22564818 |  |  | Blue
dzOssx2UEE2fZQGJQdiOoskAM4Wa | Identify the Component with Novality Function | Scope | Completed | Medium | KAVILAKSHAN V it22116338 | MEYRUSHAN N it22564818 | 03/04/2026 |  | 07/14/2025 | false | false | 03/05/2026 | KAVILAKSHAN V it22116338
fBPQPqFFCE-p4cDQv8ZntskABOtZ | Identify the Component with Novality Function | Scope | Completed | Medium |  | MEYRUSHAN N it22564818 | 03/04/2026 | 07/14/2025 |  | false | false | 03/08/2026 | LAXSHIKA.S it22596802
gWBeYnxwrkykrbEPMwE5EckAFHGf | Model Devlopment_Hydration_Component | Design | Completed | Medium | MEYRUSHAN N it22564818 | MEYRUSHAN N it22564818 | 03/04/2026 |  | 10/11/2025 | false | false | 03/05/2026 | KAVILAKSHAN V it22116338
glZVFZMC00ugyeiaqAb4OskAK3rf | Conduct needs analysis | Analysis/Software requirements | Completed | Medium |  | MEYRUSHAN N it22564818 | 03/04/2026 |  |  | false | false | 03/04/2026 | MEYRUSHAN N it22564818 | 3/3 | Evaluate information;Collect information;Prepare for data gathering | Pink
iwqmPmvSPUC9iq3fiBeaXMkAO37g | Hydation_Component_Test | Testing | Completed | Medium | MEYRUSHAN N it22564818 | MEYRUSHAN N it22564818 | 03/08/2026 |  | 02/22/2026 | false | false | 03/08/2026 | MEYRUSHAN N it22564818
k5zFgbv9SEC-JtbfZ7rYcMkAJ_RW | Mentel_Health_Component_Test | Testing | Completed | Medium | KAVILAKSHAN V it22116338 | MEYRUSHAN N it22564818 | 03/08/2026 |  | 02/22/2026 | false | false | 03/08/2026 | KAVILAKSHAN V it22116338
lEsHQqhuUEOwneKAALgHYMkAI5IK | Model Devlopment_Fitness_Component | Design | Completed | Medium | LAXSHIKA.S it22596802 | MEYRUSHAN N it22564818 | 03/04/2026 |  | 10/11/2025 | false | false | 03/08/2026 | LAXSHIKA.S it22596802
rMRkeqRTp0-3xVOG7C_BXMkAEq9J | Identify the Component with Novality Function | Scope | Completed | Medium | LAXSHIKA.S it22596802;MEYRUSHAN N it22564818 | MEYRUSHAN N it22564818 | 03/04/2026 |  | 07/14/2025 | false | false | 03/08/2026 | MEYRUSHAN N it22564818
sNhzi5I2F0e1-djQk7ewyckALfzI | Develop prototype based on specifications | Design | Completed | Medium |  | MEYRUSHAN N it22564818 | 03/04/2026 |  |  | false | false | 03/08/2026 | MEYRUSHAN N it22564818 |  |  | Yellow
u49IIJkrgEe9_LducNINZskAJRoj | Obtain user feedback | Pilot & Deployment | Completed | Medium |  | MEYRUSHAN N it22564818 | 03/04/2026 |  |  | false | false | 03/08/2026 | MEYRUSHAN N it22564818 |  |  | Pink
uUBXqlQWvkSjdBWJr-uCdMkAEOPS | Develop code | Development | Completed | Medium |  | MEYRUSHAN N it22564818 | 03/04/2026 |  |  | false | false | 03/08/2026 | MEYRUSHAN N it22564818 |  |  | Green
wLTP5ffmWkW03fjgjCVSF8kAFfpG | Deploy software | Pilot & Deployment | Completed | Medium |  | MEYRUSHAN N it22564818 | 03/04/2026 |  |  | false | false | 03/08/2026 | MEYRUSHAN N it22564818 |  |  | Green

## Plan name
Plan name | Research_Project_225
Plan ID | tLogvbp_rESwc0-JJ5J2C8kAGZeZ
Date of export | 03/08/2026